## Initial Setup Tasks
Task | Priority | Effort | Status | Assignee | Notes
Allowlist Domains | High | Low (0-4 hours) | Complete
Add CNAME for Landing Pages | High | Medium (4.5-15 hours) | In Progress
Add CNAME for Email Tracking Links | High | High (15+ hours) | Not Started
Notify Your Marketing Team | High
Contact Marketo Support to start the process of provisioning an SSL Certificate. | High
Allowlist Marketo Engage Ips | High
Set up SPF | High
Set up DKIM | High
Set up DMARC | High
Set up MX Records for Your Domain | High

## User Setup
Marketo Engage on Adobe Identify Management set-up
☛NOTE:Your new Marketo Engage subscriptions are onboarded to Adobe Identity Management System (IMS). Proceed to the following user management review in Adobe Admin Console.
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Subscription & Marketo Engage Product Admin | • Confirm you've been granted an Adobe Product Admin role by your Adobe Org System Admin. | [7 empty] | Adobe Identity Management Overview
| • If not, contact Adobe Account team or send an email to customercare@marketo.com to find out who at your organization has Adobe Admin Console System Admin privileges. | [7 empty] | Contact Adobe support
| • Accept the 'Marketo Engage Product Admin' invite to activate your Adobe ID. The welcome email is sent when the role is assigned in the Adobe Admin Console. | [7 empty] | Admin Initial Setup
Product Profiles | • Assign all desired users to the Marketo Engage Product Profile in Adobe Admin Console. | [7 empty] | Create a Product Profile
• You cannot assign users' roles in Marketo Engage > Admin > Users & Roles before adding them to a Product Profile.
• Each subscription will be a standalone Product Profile. If an undesired user is added to multiple Product Profiles (e.g., production and testing sandbox), you must delete the user from all Product Profiles. Otherwise, they will still have access to Marketo Engage.
Users | • Create a policy on when to create a user. | [7 empty] | Add or Remove a User in Adobe Admin Console
• Create a policy on when to remove users.
| • Determine who should have Adobe System Admin and Marketo Engage Product Admin permissions. | [7 empty] | Profile Levels
| • Add users to the desired Product Profile. | [7 empty] | Add or Remove a User in Adobe Admin Console
• Create one API user for each API use case.
User Management API | • Use the Adobe User Management API to invite, update, and delete users. | [7 empty] | Adobe User Management APIs
| • Use the Adobe User Management API to add or remove roles (e.g., Administrators, Support Admins, Developers). | [7 empty] | Create a support ticket with Admin Console
Product Support Administrator | • To submit a support ticket in the Adobe Admin Console, you need to have the 'Product Support Administrator' role assigned by a System Administrator to the subscriptions you manage. Only a System Administrator in your organization can assign you to this role. | [7 empty] | Create a support ticket with Admin Console
| • You might have received an email from the System Administrator stating that you are the Support Administrator for your Marketo Engage subscription. If so, click 'Get Started' in the email to join the organization. | [7 empty] | Assign the Support admin role
• Determine the appropriate contacts (with at least one backup contact) and have the System Administrator assign the Product Support Admin role accordingly.
Dynamic Chat on Adobe Identity Management Setup
☛NOTE: To use Dynamic Chat, the native conversation automation channel in Marketo Engage, proceed with the user permission setup following the steps below in the Adobe Admin Console.
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Subscription & Dynamic Chat Product Admin (if applicable) | • Accept the 'Marketo Engage Product Admin' invite to activate your Adobe ID. The welcome email is sent when the role is assigned in the Adobe Admin Console. | [7 empty] | Contact Adobe support
| • Accept the 'Dynamic Chat Product Admin' invite. The welcome email is sent when Dynamic Chat is enabled in your Marketo Engage instance and you are designated as a System Admin. | [7 empty] | Initial Setup
Product Profiles | • Assign all desired users to Dynamic Chat's Product Profile in Adobe Admin Console.
| • If an undesirable user is added to multiple Product Profiles, you must delete the user from all product profiles. Otherwise, they will still have access to Dynamic Chat. | [7 empty] | Edit Existing Permissions
| • You can edit Product Profiles in Dynamic Chat and create a custom profile with a custom set of permissions available within your subscription. | [7 empty] | List of Permissions
Users | • Create a policy on when to add and remove a chat user. | [7 empty] | Add or Remove Chat Users
• Create a policy on who should have Adobe Dynamic Chat Product Admin permissions.
• Add users to the desired Product Profile.
Set up Ongoing System Updates and Communications
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Marketo Engage Status Updates | • Subscribe to Adobe Marketo Engage Status updates. | [7 empty] | How to Subscribe to Status Page Notifications
Notifications | • Subscribe to admin notifications for critical issues such as errors in your Smart Campaigns, and critical issues found with the CRM sync. | [7 empty] | Subscribe to Notifications

## Admin Section
Roles
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Roles | • Review the prebuilt roles and confirm what permissions/access each role has.
| • Create a new role or edit the roles based on your organization's needs. | [7 empty] | Create a New Role
Edit a Role
| • Assign users to the appropriate roles. The users must be added to the subscription in Adobe Admin Console before granting their roles in Roles. Refer to the "Users' section in the Initial Setup checklist. | [7 empty] | Assign Roles to a User
• After assigning the roles for users, review the number of users per role.
• Implement a unique role for each API user for easy troubleshooting.
Sandbox (if applicable) | • Review the categories above for your sandbox. | [7 empty] | Marketo Sandbox
Workspaces & Partitions
Area | Review Focus | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Workspaces & Partitions(if applicable) | • Determine the number of workspaces and/or partitions that your organization needs to have and how many users have access to each workspace. | [7 empty] | Understanding Workspaces and Person Partitions
| • Define the primary purpose of each workspace and partition. | [7 empty] | Allow User Access to Workspace
• Define the relationship between your workspaces and partitions.
Smart Campaigns Settings
Area | Review Focus | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Smart Campaigns | • Add a restriction on Smart Campaign size, preventing accidentally emailing your entire database. | [7 empty] | Enable Person Restrictions for Smart Campaigns
Communication Limits
Area | Review Focus | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Communication Limits | • Initiate communication limits. | [7 empty] | Enable Communication Limits
• Determine if your business requires a policy on communication limits.
Tags
Area | Review Focus | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Channels | • Define how to use channels. | [7 empty] | Create a Program Channel
Tags | • Define how to use tags. | [7 empty] | Managing Tag Values
Marketing Calendar (if applicable) | • Issue Marketing Calendar seats to those who need access. | [7 empty] | Issue/Revoke a Marketing Calendar License
| • Set up the Calendar. | [7 empty] | Navigating the Marketing Calendar
Database Management
Area | Review Focus | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Field Management | • Implement a naming convention for custom fields (for example, beginning with "MKTO"). | [7 empty] | Create a Custom Field in Marketo Engage
• Be selective about the fields you sync. The more fields you sync, the slower the sync cycle will be.
| • Block updates to fields you want written to one time (e.g., original lead source, original lead source detail, first touch UTM fields, etc.). | [7 empty] | Block Updates to a Field
Custom Activities | • Define Custom Activities that are specific to your business. | [7 empty] | Understanding Custom Activities
Custom Objects | • Review how many Custom Objects you need. | [7 empty] | Understanding Marketo Custom Objects
| • Sync those Custom Objects to your CRM. | [7 empty] | SFDC Sync: Custom Object Sync
Integrations
Area | Considerations | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
CRM | • Identify the type of access you need to access your CRM. | [7 empty] | Getting started with Salesforce sync
Getting started with Microsoft Dynamics sync
| • Identify your CRM admin for troubleshooting. | [7 empty] | Understanding the Microsoft Dynamics Sync
Instructions for Creating a Custom Sync Rule
Web Services | • Determine the users/apps that can make API calls in your instance. | [7 empty] | Create an API Only User
• Review all the apps that will make API calls and determine if an increase or decrease in API calls is needed.
☛NOTE: Are you a Launch Pack customer? You can skip this step. Your consultant will provide you with an IT setup instructions document during your kickoff call.
Landing Pages | • Set up your landing page domain with a CNAME and enter domain and page information. This should be in the form: [LandingPageCNAME].[CompanyDomain].com | [7 empty] | Edit Landing Page Settings
• Choose a CNAME for your landing pages. Some examples: o * **go**.[CompanyDomain].com o * **www2**.[CompanyDomain].com o * **lp**.[CompanyDomain].com TIP: Keep it short! Shorter URLs are easier to remember. We suggest “go” as the domain.
| • Contact Marketo Support to start the process of provisioning an SSL Certificate. This process can take up to 3 business days to complete. | [7 empty] | Create a support ticket with Admin Console
• Add analytics tracking code (e.g. Google Analytics or Adobe Analytics) to your landing page templates.
☛NOTE: If you are a Launch Pack customer, please skip this step. Your consultant will provide you with Munchkin code instructions in your IT setup instructions document.
Munchkin | • Add Munchkin tracking code to your website. Munchkin code can be hard-coded or deployed via Google Tag Manager. | [7 empty] | Add Munchkin Tracking Code to Your Website
Embedding the Code
Launchpoint | • Set up LaunchPoint services for your business. Each LaunchPoint should be paired with a unique API user to aid with troubleshooting. | [7 empty] | Add Adobe Connect as a LaunchPoint Service
Interactive Webinars (if applicable) | ☛NOTE: Interactive Webinars is only provisioned to Production instances. • For creating Interactive Webinars, the built-in webinar feature, add users to the 'User' section on the Interactive Webinar tab. | [7 empty] | User and License Management
Adobe Dynamic Chat (if applicable) | • Assign users to 'Access Dynamic Chat' roles in Marketo Engage > Admin > Users & Roles. | [7 empty] | Add Dynamic Chat Access to Marketo Role
Sales Insight (if applicable) | • Set up Sales Insight Action in Sales Insight > Actions Config. | [7 empty] | Sales Insight Actions Admin Setup Guide
| • Issue seats to appropriate users. | [7 empty] | Invite Individual Users to MSI Actions
| • Configure the API. | [7 empty] | Marketo Sales Insight Configuration Tab in Salesforce
| • Customize the lead scores. | [7 empty] | Priority, Urgency, Relative Score, and Best Bets
Sales Connect (if applicable) | • Invite the appropriate Marketo Engage admins to the Sales Connect instance. | [7 empty] | Accessing Your New Sales Connect Instance
| • Complete the additional Sales Connect admin setup in Sales Connect and Salesforce. | [7 empty] | Inviting and Managing Users
Webhooks (if applicable) | • Create any required Webhooks for your business. | [7 empty] | Create a Webhook
Treasure Chest
Area | Considerations | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Treasure Chest | • Enable Treasure Chest to experiment with piloting features. | [7 empty] | Enable or Disable Treasure Chest Features
• Determine the features that you want to turn on or off.
Campaign Inspector | • Turn on Campaign Inspector to view all your Smart Campaigns at once. | [7 empty] | Enable Campaign Inspector

## Database
System Smart Lists
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
All People | • Determine implementing a 1:1 sync with your CRM or applying filters to limit who moves from system to system and when.
| • Review the total number of people and marketable people in your Marketo Engage database. | [7 empty] | Database Dashboard
Blocklist | • Define blocklist criteria. Consider adding competitor's domains to the blocklist to prevent them from receiving any of your emails. | [7 empty] | Add Person to Blocklist
Marketing Suspended | • Define Marketing Suspended criteria. | [7 empty] | Marketing Suspended
Bounced Email Addresses | • Define your criteria for bounced email addresses.
| • Review the people in Email Invalid category and if their emails need be manually reset. | [7 empty] | Hard and Soft Bounces in Emails
Possible Duplicates | • Review People in the Possible Duplicates list.
| • Define your duplicate management strategy to determine if you want to merge people manually. | [7 empty] | Find and Merge Duplicate People
• If you have a CRM integration, define a process and account for the effect of merging leads in your CRM.
No Acquisition Program | • Establish campaigns in your program templates that set an Acquisition Program, especially if using global forms. | [7 empty] | Acquisition Program
Unsubscribed People | • Review your criteria for Unsubscribed People. | [7 empty] | Understanding Unsubscribe
Group Smart Lists
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Group Smart Lists | • Be aware of creating Group Smart Lists so that there aren't duplicate lists.
• Keep track of the master lists in the database.
Segmentations
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Segmentations | • Create segmentations based on your business needs. Each subscription is limited to 20 segmentations and 100 segments within each segmentation. | [7 empty] | Create a Segmentation

## Marketing Activities
Organization
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Naming Conventions | • Define a consistent naming convention for your subscription prior to building out folder structure. | [7 empty] | Naming Schemes
Folder Structure | • Build a consistent and easily navigable folder structure by referencing this example. | [7 empty] | Understanding Folders
Programs | • Create program templates for each channel you have created in your admin section. You can start by importing programs from the Program Library. See specifics in the "Assets" table below. | [7 empty] | Create a Program Channel
Import a Program
| • Determine which flow steps of the Smart Campaigns can be in a global program vs. a local program. | [7 empty] | Add a Flow Step to a Smart Campaign
• Include acquisition, membership, and success tracking as part of your program template to standardize the process.
Archive | • Determine a policy on when to archive programs and assets. Note that once archived, it removes items from select lists as well as reporting. | [7 empty] | Archive a Folder
Notifications | • Subscribe to Notifications. | [7 empty] | Subscribe to Notifications
Assets
☛NOTE: To store marketing assets like programs, Landing Pages, and emails in separate areas, please reference the Admin section checklist to learn how to set up Workspaces.
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Program Types | • Understand the Four program types. | [7 empty] | Understanding Programs
| • Import program templates from the Program Library to start. | [7 empty] | Import a Program
Program Import Library Overview
| • Create an Interactive Webinar, the built-in webinar platform, using an Event Program and associate a room with the Interactive Webinar program (recommended). | [7 empty] | Enable Communication Limits
| • Set up scoring programs to watch for buying signals on your website and with your content. | [7 empty] | Create an Interactive Webinar
Designing Interactive Webinars
Tokens | • Set up Tokens. | [7 empty] | Understanding My Tokens in a Program
| • Use tokens in regularly used program types to increase efficiency. Consider implementing tokens that the organization regularly needs in the global folder. | [7 empty] | Nesting Tokens
Batch Campaigns | • Set up Batch Smart Campaigns with filters in the Smart List section. | [7 empty] | Batch Campaign
• Schedule the Smart Campaigns for recurrences such as daily, weekly, and monthly.
Trigger Campaigns | • Set up Trigger Smart Campaigns by using at least one trigger within the Smart List section. | [7 empty] | Trigger Campaign
• Activate the Smart Campaigns in the 'Schedule' tab to run the campaign actions.
Landing Pages | • Create a free-form landing page template or a guided landing page template for program use. | [7 empty] | Create a Free-form Landing Page Template
Create a Guided Landing Page
Local Forms | • Define your forms strategy for global forms vs. local forms. | [7 empty] | Create a Form
• To use global forms, use Smart Campaigns to set Acquisition Program for reporting, and use referrer details to assign people to programs/campaigns appropriately.
Smart List Subscriptions | • Set up Smart List Subscriptions in Marketing Activities or Database for reports you'd like to receive daily, weekly or monthly such as like email performance and person performance, etc. | [7 empty] | Edit a Smart List Subscription
Manage Report Subscriptions | • Set up report subscriptions in Marketing Activities or Analytics to basic reports or Revenue Cycle Explorer reports, etc. | [7 empty] | Manage Report Subscriptions
Subscribe to a Basic Report
Subscribe to a Revenue Explorer Report
Operational Programs
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Person Scoring | • Implement a tokenized lead/person scoring program. Breakout both behavior and demographic scores from the general Person Score. | [7 empty] | OP-Scoring-Behavior
OP-Scoring-Demographic
| • Import a scoring program from the Marketo Program Library to start. | [7 empty] | Import a Program
Person Source | • Create a centralized program that assigns values to lead/person source in System Managed fields.
| • Import an Operational Data Management program from the Marketo Program Library to start. | [7 empty] | OP-Data Management
Data Standardization | • Create a centralized program to standardize incoming data.
| • Import an Operational Data Management program from the Marketo Program Library to start. | [7 empty] | OP-Data Management
Bounce Management | • Create an Operational program for bounce management to capture all bounce details.
| • Import a Deliverability Management program from the Marketo Program Library to start. | [7 empty] | OP-Deliverability Management
Privacy & Compliance | • Create programs to ensure you're compliant with data privacy and spam laws such as GDPR, CASL, CAN-SPAM, CCPA, etc. ☛NOTE: Always remember to consult your legal team on these issues. Ask your team about previous initiatives to maintain compliance before making any changes. | [7 empty] | The GDPR and The Marketer: A Practical Guide for the Marketo Customer
Lifecycle | • Create a program to move leads through your Lead Lifecycle by updating the values for Person Status.
| • Import a Lead Management program from the Marketo Program Library to start. | [7 empty] | OP-Lead Management
Interesting Moments (if applicable) | • Create a centralized Smart Campaign that communicates relevant information to your sales team via the Marketo Sales Insights app. | [7 empty] | How do I create an interesting moment?
Subscription/Preference Center | • Set up a Subscription/Preference Center and the landing page within Marketo Engage(if applicable). ☛TIP: As there is no one way to set this up, it's recommended to visit the Marketing Nation Community and search "Subscription Center" to see the different methods your peers are using and choose the one best suited to your needs. | [7 empty] | How to set up and manage a subscription center
Email Deliverability | • Create an Email Performance Report for monitoring email sends and the deliverability trends. | [7 empty] | Email Performance Report

## Design Studio
Landing Pages
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Global Landing Pages | • Create global Landing Pages (free-form/guided). | [7 empty] | Understanding Free-form vs Guided Landing Pages
| • Create a test page to A/B test the winning Landing Page template (if applicable). | [7 empty] | Landing Page Test Groups
Templates | • Create a design for global Landing Pages.
Privacy & Compliance | • Create a footer using Snippets or Tokens in your Landing Pages for privacy compliance. | [7 empty] | Add a Snippet to a Landing Page
Add Text and Tokens to a Landing Page
Forms
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Global Forms | • Set up global forms for use cases such as subscription preferences, gated content downloads, demo requests, webinar registrations, etc. | [7 empty] | Create a Form
Privacy & Compliance | • Keep your forms GDPR compliant. | [7 empty] | The GDPR and The Marketer: A Practical Guide for the Marketo Customer
Data Standardization | • Consider applying picklists to the form fields instead of open text fields to prevent messy data. | [7 empty] | Add a Field to a Form
Emails
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Global Emails | • Create global emails. | [7 empty] | Create an Email
Templates | • Design a module-based email template with a designer/developer, or use your own HTML. | [7 empty] | Create an Email Template
• Create a tested email template to A/B test the winning template (if applicable)
Privacy & Compliance | • Add Snippets to your email templates to control reusable blocks such as copyright year, global location, and compliance-specific language. | [7 empty] | Add a Snippet to an Email
| • Add Tokens to personalize content based on the target audience. | [7 empty] | Add an Email Script Token to Your Email
Snippets
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Snippets | • Create Snippets to have reusable content blocks that can be used for multiple use cases, such as contact information, social media links, brand information, and privacy and compliance notes in your emails and Landing Pages. | [7 empty] | Create a Snippet
Images & Files
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Naming Conventions | • Use consistent naming conventions for images and files. Examples: File Naming Convention: Asset Type-Asset Name (Ex: White-Paper-Evaluating-Cloud-Computing-Get-Your-Board-on-Board) Image Naming Convention: Image Type-Asset Type-Asset Name (Ex: Thumbnail-White-Paper-Evaluating-Cloud-Computing-Get-Your-Board-on-Board) | [7 empty] | Add Images and Files to Marketo Engage
Organization
Area | Action Item | Date of Completion | URL in the Instance | Priority | Effort | Status | Assignee | Notes | Resources
Folder Structure | • Create subfolders for each type of asset and organize global assets (e.g., conversational flows, email templates, emails, forms, images and files, Landing Pages, Landing Page templates, snippets, etc.) appropriately. | [7 empty] | Organize Your Images and Files Using Folders

## Document your setup
Data
Area | Action Item | Date of Completion | Priority | Effort | Status | Assignee | Notes | Resources
List Import | • Gather a list of data sources that records will be pulled from to import into Marketo Engage. | [6 empty] | Import a List of People
| • If you are importing from multiple data sources, consider using Master Lists or creating a Custom Field on the person record to denote the data source. | [6 empty] | Create a Custom Field in Marketo
Database Integration | • If leveraging the native sync between Marketo Engage and your CRM, carefully consider what fields you want to sync between systems. Not every field needs to be synced, so be strategic about your data flows.
Documentation
Area | Review Focus | Date Reviewed | Priority | Effort | Status | Assignee | Notes | Resources
Users & Roles | • Document the current users in your instance for safety reasons. The following details should be included at a minimum (and are all visible and downloadable by going to Admin > Users & Roles): - Name - Email - Login - Role - Access Expiration Date - User Created Date - Most Recent Log In Date | [6 empty] | Export a List of Users and Roles
| • As a Marketo Engage Product Admin, develop an internal process to audit and update the Marketo Engage user list at a regular cadency. To make changes to the list of users in Adobe Admin Console, consider bulk actions, such as uploading a .CSV, using the User Management REST API, etc. | [6 empty] | CSV Bulk upload
Organization | • Document the agreed folder structure, standard naming conventions for programs, assets, etc, and the why behind the decisions made. | [6 empty] | Best practices to organize a new Marketo Engage instance
Workspaces & Partitions | • How are Workspaces and Partitions defined?
• What is your process to add Workspaces to your instance or add users to a Workspace?
Changelog | • Create a changelog where you can document what's changing in your instance and the why of the modifications. | [6 empty] | Develop an instance governance guide with documentation
Playbooks | • Create a User Playbook or Admin Playbook for internal users onboarding to the instance.
Conversations with internal teams | • Start to align the internal marketing team's expectations of Marketo Engage with Marketo Engage's capabilities.
• Identify the teams that will be your stakeholders in the Marketo Engage instance and document their goals to achieve using Marketo Engage as a technology.